## Slide 1: CommScope: Remediation Engagement Internal Kickoff Phase 2 July 2023

## Slide 2: Agenda
Introductions
Engagement scope & approach
Collaboration requirements
Principals and rules of engagement
Next steps

## Slide 3
ENGAGEMENT LEAD
As needed
SUBJECT MATTER EXPERTS
PROJECT MANAGEMENT
GOVERNANCE TEAM
CYBER DEFENSE AND ARCHITECTURE TEAM
ENGAGEMENT OVERSIGHT
Team Introductions
Briefly introduce yourself.
Name
Position
Years of service
Role within the organization
Experience with cybersecurity

## Slide 4
CommScope Recap

## Slide 5: Attack Lifecyle
February – March 2023
Initial Recon
Initial Compromise
Establish Foothold
Complete Mission
Escalate Privileges
Internal Reconnaissance
Move Laterally
Maintain Presence
Account compromise
Single Factor Authenticated Remote login to Citrix
March 8, 2023
Kerberoasting
March 8, 2023
Move to ARRS domain
March 9, 2023
Install backdoor
March 9, 2023
Data collections / Data exfil (w.ps1)
Data encryption/ransomware (ESXi hypervisors)
March 26, 2023
Discovery of Attack Surface Area.
Feb 22.2023
Use of collected credentials
March 11, 2023
Domain Discovery
Collection of NTDS.dit and security hives*
March 11, 2023
*Attacker performed the cycle of credential harvesting on 4 domains (ARRS, CommScope, MFG, USA)
Mandiant Proprietary and Confidential

## Slide 6: Summary of Mitigation and Hardening
CommScope information security took the following mitigation and environmental hardening procedures to contain, eliminate, and prevent the threat actors continued activities:
Reset all user and service credentials
Reset the Kerberos Account (KRBTGT), twice
Create all new privileged user or service accounts
Enable Multi-Factor authentication for all users, all access points
Block known threat actor IP addresses at the firewalls
Block execution of known host-based Indicators of Compromise (IOC) within the deployed EDR, SentinelOne
Deploy addition security tools, Trellix HX, to all systems and enable Mandiant Managed Defense services
Rebuild/Restore Microsoft Active Directory architecture to a known good state
Apply hardening polices to the new Microsoft Active Directory architecture
Rebuild VMWare ESXi hypervisors, apply hardening polices
Mandiant Proprietary and Confidential

## Slide 7: Lesson Learned
Key areas of improvement for CommScope Cyber Security Program
Global use of Multi-Factor Authentication on all systems
Standardized log collection
Standardized security tool configurations / processes / procedures
  EDR
  Firewall (IPS/IDS)
Maturing of Security Team
  Education and Training for security professionals on documented defense tools, techniques and procedures
  Documented and current SOC plans / playbooks / procedures
Mandiant Proprietary and Confidential

## Slide 8
Remediation Charter

## Slide 9: Scope of Remediation Project
The client has many cybersecurity projects in flight.
Managing the projects, monitoring project status, and achieving meaningful progress is their primary issue.
The secondary problem is reporting project status to their SLT. The SLT and the BoD are hyper-focused on Cybersecurity project progress.
AzureDevOps (ADO) is the chosen project tracking tool.
There are about 6 work-streams that have been identified.

## Slide 10: High-level Timeline
Cybersecurity
Infrastructure
Program Increment 1
Org Charters & SteerCO
PMO design & deploy*
Remediation Workstreams
Governance
0 to 90 Days
90-115
Jul 2023
Project Kickoff
Project Management
Identify and Access Management
Program Increment 2
Sep 2023
Project Charters & Requirements
Execution Monitoring
*Release plans developed for each initiative
Product Security
Other Security Initiatives
Data Security

## Slide 11: Current Status
Ready
In Progress
Done
Provide Mandiant Admin Access at Project Level
Accepted
Determine Recurring Weekly Status Meetings
Create Project Charter
Backlog
Decide on Collaboration Approaches
Review WIP & Plan Future Work
Develop Remediation Backlog
ADO imported with EPICS/Features/Stories/ Tasks
CPA Onboarding to the project: CommScope tools Access

## Slide 12: Standup Meeting Overview
Currently scheduled Mon, Tue, Wed, Thu and Fri at 9AM Eastern
Objectives
  Review the ADO Kanban board in order to share and discuss:
    Daily updates and progress
    Next steps and priorities
    New or persistent risks, issues, or blockers
  Things that could be brought up.
    Information/updates from CommScope that could be useful to the team.
    Escalations
    Resourcing requirements/challenges
    Changes in priority

## Slide 13: Proposed Meeting Schedule
Monday | Tuesday | Wednesday | Thursday | Friday
Daily Standup (30 Minutes) Capacity Planning?? (30 minutes) | Daily Standup (30 Minutes) Release Planning?? (1 hour) | Daily Standup (30 Minutes) Backlog Refinement?? (1 hour) | Daily Standup (30 Minutes) Leadership Status Meeting?? (1 hour) | Daily Standup (30 Minutes)
Week 1 | Week 2 | Week 3 | Week 4
 |  | Project Stakeholder Meeting (1 hour) | Cyber Steering Committee Meeting (1 hour)
Daily Standup
Attendees: Core + CPA Team
Agenda: Discuss roadblocks, Inhibitors, changes to AC
Capacity Planning
Attendees: Core Team
Agenda: Capture changes in availability, estimates, assign work category
Backlog Refinement
Attendees: Core/Governance Team
Agenda: Refine stories, estimate effort, resolve dependencies, prioritize work
Leadership Status Meeting
Attendees: Delivery Team & Leadership
Agenda: Status review, challenges, priorities & decisions
Release Planning
Attendees: PMO/Governance Team
Agenda: Define release goal, prioritize work, set dates, & validate charter
Project Stakeholder Meeting
Attendees: CommScope & Mandiant Stakeholders
Agenda: Discuss status of Mandiant deliverables as defined in the SOW
Steering Committee Meeting
Attendees: Steering Committee & Leadership
Agenda: Discuss status of project relative to project charter definitions

## Slide 14: Next Steps

## Slide 15
Discussion